## Business trip budget
Phase number | Phase name | Headlines | Technical Steps | Responsiple | Date | Status
Phase 1 | Pre-Deployment & Planning | Define architecture, security, and cost baseline | Architecture design workshop with stakeholders | Both | 2026-02-01 | Done
|  |  | Define IP addressing plan and naming conventions | Both | 2026-02-01 | Done
|  |  | Design security framework and RBAC model | Both | 2026-02-01 | Done
|  |  | Cost estimation using Azure Pricing Calculator | Both | 2026-02-01 | Done
|  |  | Budget review and approval | Both | 2026-02-01 | Done
Phase 2 | Network Infrastructure Deployment | Build secure multi-region hub & spoke connectivity | Deploy Hub VNet with VPN Gateway (UK South) | Both | 2026-06-01 | Done
|  |  | Deploy Spoke VNets with VPN Gateways (North Europe, West Europe) | Both | 2026-06-01 | Done
|  |  | Configure Site-to-Site VPN tunnels (Hub ↔ Spokes) | Both | 2026-06-01 | Done
|  |  | Deploy Azure Firewall and configure security policies | Both | 2026-06-01 | Done
|  |  | Deploy Private DNS Zones and link Vnets | Both | 2026-06-01 | Done
Phase 3 | Application & Data Platform | Deploy global application and resilient data layer | Deploy Azure Front Door with WAF configuration | Both | 2026-09-01 | Done
|  |  | Deploy Application Gateways (WAF v2) in both regions | Both | 2026-09-01 | Done
|  |  | Deploy App Service Plans and App Services (Premium v3) | Both | 2026-09-01 | Done
|  |  | Configure VNet Integration and Private Endpoints | Both | 2026-09-01 | Done
|  |  | Deploy Azure SQL Databases in both regions | Both | 2026-09-01 | Done
|  |  | Configure Active Geo-Replication and Failover Groups | Both | 2026-09-01 | Done
|  |  | Deploy Azure Key Vaults and migrate secrets | Both | 2026-09-01 | Done
Phase 4 | Security, Monitoring & Operations | Enable monitoring, threat protection, and operational readiness | Deploy Log Analytics Workspace in Hub | Both | 2026-11-01 | Done
|  |  | Enable Microsoft Defender for Cloud | Both | 2026-11-01 | Done
|  |  | Configure Azure Monitor alerts (performance, availability, security) | Both | 2026-11-01 | Done
|  |  | Enable Azure DDoS Protection Standard | Both | 2026-11-01 | Done
|  |  | Perform security assessment and remediation | Both | 2026-11-01 | Done
|  |  | Documentation and knowledge transfer | Both | 2026-11-01 | Done
Phase 5 | Testing, Failover & Go-Live | Validate resilience and move to production | End-to-end functional testing | Both | 2026-12-01 | Done
|  |  | Performance and load testing | Both | 2026-12-01 | Done
|  |  | Failover testing (Azure SQL, Front Door) | Both | 2026-12-01 | Done
|  |  | Production cutover and DNS switch | Both | 2026-12-01 | Done